## Slide 1: THE ETHIOPIA CAPITAL MARKETS DEVELOPMENT AGENDA: PROGRESS AND PROSPECTS
Capital Markets Project Implementation Team (CMPIT)
National Bank of Ethiopia
January 2022

## Slide 2: Outline
Ongoing and Planned Activities
A Roadmap for Development of Financial Markets
Progress in Implementing the Financial Markets Reform
How to Get Involved
Background

## Slide 3
Background⏤ Developing financial markets is one of the priorities of the HERP
Capital markets help mobilize domestic saving thereby
  Creating liquidity in the economy, and
  Reducing the need for reliance on foreign capital
Capital markets help investors raise long-term finance for investment
  The Ethiopian economy still relies on traditional bank financing; but banks intermediate mostly short-term financing
Markets foster price discovery and allocate finance more efficiently in the economy
Capital markets help improve macroeconomic and risk management
Hence, development of financial markets would help achieve the HERP objectives of correcting macroeconomic imbalances, rebalancing growth, and enhancing productivity

## Slide 4
1. Money Markets
Developing T-bills market
Develop interbank money markets
2. Launching a Securities Exchange
Secondary markets for equities and T-bills
Basic derivatives (FX and commodity futures)
3. Deepening the Markets
Developing markets for corporate bonds, ABSs, and other advanced derivatives
0. Liberalization
Financial sector open to the Diaspora
NBE bills repealed
T-bills market liberalized
A Roadmap for Development of Capital Markets

## Slide 5
8
Progress in Implementing the Capital Markets Development Plan
CM Proclamation enacted
1
Legal framework for establishment of key institutions
Legal framework for issuance and trading of securities
Capacity building
2
Training and certification program launched with support from FSD Africa
CMPIT established
3
The team has 13 full-time experts, including experts with international experience in securities law and capital markets
About 280 professionals participated so far, o/w 50 have progressed to level 3
NBE established a project team (CMPIT) with funding from development
Legal basis for regulating and supervising operators and securities transactions
Currently registering about 230 professionals
Initially offered to intuitions, but now open to individuals through competitive applications
Project office located in the 11th floor of Hibret bank HQ

## Slide 6
8
Ongoing and Planned Activities
CMPIT Working on
Drafting of detailed regulatory framework (Directives and Regulations)
Efforts underway to launch an ESX project team
ESX will be established as a PPP-based share company
Enhancing capacity development efforts
An ESX project team will be established to form the company and promote it to investors
Ongoing training and certification of professionals will be enhanced
Setting up the Capital Markets Authority
Capacity development and investor education strategy
Developing CMA’s near-term action plan and medium-term strategy
Long-term capital markets development roadmap
Research and analyses on enabling environment
The design of the ESX
However, priority will be for local investors to have a majority share
Well-established global exchanges already expressing interest to take part in the ESX
A 2-days IPO workshop for potential issuers (companies) planned to be held in March/April in collaboration with Standard Bank
Near-term plan is to launch a program for training of trainers
Long-term plan is to develop local capacity for training by strengthen the capacity of the Institute of Financial Studies and coordinate with academic institutions

## Slide 7
8
How to Get Involved?
Actively participate in stakeholder consultations
Take part in capacity development efforts
Aspiring capital markets service providers/professionals
Invest in ESX when launched
Financial institutions
The CMPIT and the future CMA will be reaching out to potential stakeholders for consultation on the regulatory framework and market development strategies
Actively participate in such consultations to shape the future of the Ethiopian capital markets
Be the first to list your company on the Exchange
Potential IPO issuers
Academic and training institutions
Potential investors
Future market intermediaries
Even individual investors
Financial institutions
MNCs
Non-financial PLCs

## Slide 8
THANK YOU
Questions and Comments are Welcome